DRAFT MINUTES for Comment

Brassica rapa Genome Sequencing Project (BrGSP) Meeting

10 am Sunday 15 January 2006, San Diego

Esquire Room in the Town & Country Hotel, San Diego

Minutes taken by Y.P. Lim (Chungnam National University)

Attending:

| Australia | Ross Chapman | ross.chapman@dpi.vic.gov.au | AgVic |
| --- | --- | --- | --- |
| Canada | Isobel Parkin | parkini@agr.gc.ca | AAFC |
|  | Andrew Sharpe | sharpea@agr.gc.ca | AAFC |
|  | Wilf Keller | Wilf.Keller@nrc-cnrc.gc.ca | NRC |
|  | Raju Datla | raju.datla@nrc-cnrc.gc.ca | NRC |
| China | Bin Liu | liub@genomics.org.cn | BGI |
| France | Anne-Marie Chevre | anne-marie.chevre@rennes.inra.fr | INRA, Rennes |
|  | Boulos Chalhoub | chalhoub@evry.inra.fr | INRA Evry |
| Germany | Daniela | dholtgra@CeBiTec.Uni-Bielefeld.de | Bielefeld |
|  | Christian Obermeier | christian.obermeier@agrar.uni-giessen.de | Giessen |
| Korea | Yong-Pyo Lim (CHAIR) | yplim@cnu.ac.kr | Chungnam |
|  | Myung-Ho Lim |  | NIAB |
|  | Tae-Jin Yang | tjyang@rda.go.kr | NIAB |
|  | Soo-Jin Kwon |  | NIAB |
| UK | Graham King | graham.king@bbsrc.ac.uk | Rothamsted Research |
|  | Ian Bancroft | ian.bancroft@bbsrc.ac.uk | JIC |
| USA | Andy Paterson | paterson@dogwood.botany.uga.edu | Georgia |
|  | Chris Pires | piresjc@missouri.edu | Missouri |
|  | Carlos Quiros | cfquiros@ucdavis.edu | UC Davis |
|  | Chris Town | cdtown@tigr.org | TIGR |
|  | Joanna Friesner | jdfriesner@stanford.edu | MASC (Arabidopsis) |

- Invitation to the BrGSP workshop in Korea (June 14-16, 2006)

- Chungmu Marine Hotel, TongYoung, South Ocean side in Korea

- Members involved in B. rapa sequencing in each country: Invitation letter will be send later.

- Schedule has to be discussed with Canada group

- The progress of sequencing and anchoring of 600 seed BACs will be announced at the workshop.

Dr. Wilf Keller informed the meeting that the Fourth Canadian Plant Genomics Workshop will be held June 19-21, in Ottawa, Ontario (http://cpgw.ca).

2. BAC-end data  
    a) Sequencing status

Current Status of BAC end sequencing in MBGP

| -YPL asked Dr. Wilf Keller, Canada, if there was additional capacity in Genome Canada program to end-sequence the remaining non-allocated BAC clones ( KBrH16-50, KBrB97-132) : need to be reconsidered Plates | No. clones | Group | Country | Status |
| --- | --- | --- | --- | --- |
| KBrH001 - KBrH015 | 5,760 | NIAB | S. Korea | completed |
| KBrH016 - KBrH050 | 13,440 | AAFC + NRC | Canada | underway |
| KBrH051 - KBrH062 | 4,608 | JIC | UK | completed |
| KBrH063 - KBrH087 | 9,600 | DPI | Australia | completed |
| KBrH088 - KBrH117 | 11,520 | JIC, Bath | UK | completed |
| KBrH118 - KBrH136 | 7,296 | U. Bielefeld | Germany | completed |
| KBrH137 - KBrH144 | 3,072 | CNU | S. Korea | completed |
| KBrB001 - KBrB096 | 36,864 | NIAB, CNU | S. Korea | completed |
| KBrB097 - KBrB132 | 13,824 | unallocated |  | - |

For end-sequencing of non-allocated BAC clones (KBrH 16-50 and KBrB97-132), Dr. Wilf Keller indicated that he can discuss this issue with YPL in Saskatoon in late March.

b) Status of the submission to GenBank and notify community

- At this moment 133,617 BAC end sequences are registered in GenBank

- The registration format of BAC end sequence should be harmonized. Need to make an ideal format and unification.

- Quality issue need to be discussed for the registration of BAC end sequences (TJ Yang)

Action

- YPL: should discuss with Dr. Wilf Keller on sequencing of unallocated BAC clones.

- YPL: should send BAC library(ies) to Wilf Keller or Isobel Parkin

3.      Status of seed BAC sequencing 
NIAB(Korea):

- First phase sequence of about 600 BAC clones are obtained. Ordered contig sequences (phase II) for the BACs will be ready by June 2006.

- Sequence-based mapping of the seed BAC are on-going

- Hope to finish map all the BACs by June

- The progress of sequencing and anchoring of 600 seed BACs will be announced at the workshop in June 2006 in Korea.

- Pioneer walking for cytogenetic chromosome 1 (R9) will be shown at the Workshop.

- Seed BAC information will be announced with the related BACs based on BAC end match and SnaPShot fingerprinting contig information.

Australia

- First phase sequence of 5 BAC clones are obtained.

- Hope to finish 100 BAC clones within 6 months

Action:

- The information on target clone number for sequencing in Australia should be discussed with YPL or NIAB to avoid any overlap of sequencing between Korea and Australia

4.      Release Policy

- BAC submission policy for trace files and annotation of BAC sequence

- rapa ssp. pekinensis (Chinese cabbage) inbred line Chiifu-401 libraries KBrH (56,592 clones) and KBrB (50,688 clones)

- KBrH001A01 to KBrH148P24 for HindIII BAC library

- KBrB001A01 to KBrB132P24 for BamH1 BAC library

- Sequencing from forward (f) and reverse (r) direction

- KBrH001A01 (BAC clone ID) + R (reverse)/ F (forward)

- Proposed standardisation of submission form for BAC-end sequences in the GSS division of GenBank  (Example: see appendix end of this document)

5. Nomenclature of Brassica Genetic loci

- It was agreed that where possible, the project participants should aim for standardisation of genetic locus nomenclature conventions. Following agreement amongst the wider community, this could also be adopted for wider integration of different genetic linkage maps.

- A proposed nomenclature system had been developed by GJK and G. Teakle and will be published for the initial reference CKDH linkage map (Choi et al.).  This included recommendations for standardisation previously proposed by IPGRI (http://www.ipgri.cgiar.org/publications/pdf/913.pdf).

- This will accommodate existing locus names with the least amount of confusion possible while still adhering to this system. Use of an institute code facilitates avoiding the same locus name being used on different occasions when they might in fact represent different loci (homonyms).

- This proposed convention will be posted on www.brassica.info and sent for review and comment to all authors of the CK mapping project.

- The manner in which this is applied this to markers generated by the different labs (i.e. assingment of synonyms) also needs to be reviewed by the respective labs.

- Once approved, this will be published as the recommended format for Brassica locus nomenclature, both on the www.brassica.info website and hopefully as part of a journal publication.

5.   Next phase of sequencing by BAC-by-BAC of each chromosome to Phase II 
Proposed allocation of B. rapa chromosomes to each country (subject to notification and confirmation to YPL)

| Chromosome | Country | PI | Status | Completion |
| --- | --- | --- | --- | --- |
| R1 | UK/China | Bancroft/Meng | Proposed | 2009 |
| R2 | Australia | Edwards [any chr.] | In preparation | 2009 |
| R3 | Korea | Park | Funded | 2008 |
| R4 | USA | Paterson [any chr.] | To be submitted 2006 | 2009 |
| R5 | Canada | Keller [any chromosome] | In preparation | 2009 |
| R6 | Canada | Keller [any chromosome] | In preparation | 2009 |
| R7 | Canada | Keller [any chromosome] | In preparation | 2009 |
| R8 | UK/China | Bancroft/Meng | Proposed | 2009 |
| R9 | Korea | Park | Under way | 2007 |
| R10 | France/Germany | Chalhoub/Weisshaar [any] | To be submitted 2006 | 2009 |

- Discussion of sequencing project and plans

6. Genetic anchoring of sequenced BACs 
 A. Status of the Reference Map of Chinese Cabbage in CKDH population (CNU, WHRI/Res, AAFC, AgVic)

    - In the reference genetic map, there are a total of 10 linkage groups.

    - The map currently consists of 278 AFLP, 236 SSR, 25 RAPD, 18 ESTP, 3 STS, 5 PCR-RFLP, and 3 CAPs markers.

        - Development of Additonal Genetic Map in CKRI population (since from the same parents as CKDH, the maps can be merged) (CNU)

    - 153 F8, 83 F7, and 5 F6 lines of CKRI population were produced.

    - Using 52 F7 plants of CKRI, SSR markers located at regular intervals in CKDH map are mapping in CKRI for the pilot experiment of CKRI.

- Genetic Anchoring of Sequenced BAC (500 Seed BACs)

- CNU: 151 SSR markers for the sequenced 260 seed BAC clones were developed.  SSR markers will be mapped in CKDH population.

- NIAB: 119 SSR markers for the 240(?) seed BAC clones were developed.

- Development of SSR Markers from BAC-end Sequences (BES)

- CNU: In 2006, 300 SSR markers will be generated from BES of HindIII and BamH1 libraries.

Additional anchor-mapping of BACs is being carried out by NIAB in the JWF3 Chinese cabbbage population - this requires integration with CKDH to provide a consistent set of chromosome 'bins'.

______________________________________________________

- Appendix:   Proposed standardisation of submission form for BAC-end sequences in the GSS division of GenBank

- ||
TYPE: Pub
TITLE: End sequence of Brassica rapa HindIII (KBrH) BAC clone

AUTHORS: Yang, T.J., Kwon, S.J., Kim, J.A, Kim, J.S., Lim, K.B., Jin, M, Park, J.Y., Lim, M.H., Kim, H.I., Hong, C.P., Lim, Y.P., Park, B.S.      
YEAR: 2004
STATUS:1
||
TYPE: Lib
NAME: KBrH, Brassica rapa HindIII BAC library
ORGANISM: Brassica rapa ssp. pekinensis
CULTIVAR: Chiifu
HOST: E. coli DH10B
VECTOR: pCUGIBac1
V_TYPE: BAC
RE_1: HindIII 
DESCR: Brassica rapa spp. pekinensis inbred line Chiifu BAC library (KBrH BAC) is provided by Yong-Pyo Lim.
||
TYPE: Cont
NAME: Beom-Seok Park
FAX: +82-31-299-1672
TEL: +82-31-299-1670  
EMAIL: pbeom@rda.go.kr
LAB: Brassica Genomics Team
INST: National Institute of Agricultural Biotechnology
ADDR: 225 Seodun-Dong, Suwon, 441-707, Korea
||
TYPE: GSS
STATUS: New
CONT_NAME: Beom-Seok Park
GSS#: KBrH001A01F
CLONE: KBrH001A01
SEQ_PRIMER: T7
DNA_TYPE: Genomic
CLASS: BAC ends
PUBLIC:
LIBRARY: KBrH, Brassica rapa HindIII BAC library 
COMMENT: BAC end sequence of Brassica rapa ssp. pekinensis HindIII BAC clone KBrH001A01
SEQUENCE:
CAAGAAAAACATTGTAATGATTGCTAATCAACTATATTCTTCTCGTGGCA
ATTTGTTGATCGAATGTAGTGATAACAAGGGGAAATTTTCATCTAATCTG
TTAAGTTTCGATGCAAATCCGTTTATCATTTCTTTCAGCGACTATAAATG
GCCAAAAGAAACACGATGGGATTGCACTATTAGTCATGGAGAGAATAATA
AGTTCTATTATGATCTTCAAGTATATCATGCAAATTATCAACGATGTGGT
CAGTTACGTTCATGGATTGCCAAAGATGATGGAATTTGGTTTACAGAAAG
ATATGAAGATCCAGCAGGGTTTGTTTTACCTTGGAAAACACGTGCCTAGT
TTTCTGTTTTACTTTGTTCTTACAATAACTACAAACATTAAATAAAATAA
ATCGATTTTGCTTTAAGTTTGTTGAAAAAAAAAATATAAAATAAGATATC
TCAATTCTATAATACATAAAAGAATTACATTGCCTATTCTACACATCTTA
TTATATAAATCTTGGTTCTACAAAGTTGTTAATTAACATGATCGCGACAT
GTGTCAATAAATTTTTTTAAAATTGCGACATGTGTCAAAAATATGATCTA
TTTTCTTAAGATTTAAAAGAGATTTAGAAAATAGAAGTTATTATTACAAA
ATATATCTTTTTACCATTCTTGTTAAGATTATGGAAAATAACGATTACTA
TTACATAGTCTTTTATATTATATATT
||
TYPE: GSS
STATUS: New
CONT_NAME: Beom-Seok Park
GSS#: KBrH001A01R
CLONE: KBrH001A01
SEQ_PRIMER: M13 Reverse
DNA_TYPE: Genomic
CLASS: BAC ends
PUBLIC:
LIBRARY: KBrH, Brassica rapa HindIII BAC library 
COMMENT: BAC end sequence of Brassica rapa ssp. pekinensis HindIII BAC clone KBrH001A01
SEQUENCE:
ACAATGAACGTTAAGGTACCTAGCTTAGTTCTTCTTTTTGTGGTTGTTAA
GGCTCGAATTATGAACGTTACGTAGGTGAAAGTGGAACATTCGTAAGTAC
ACAAAAATGTGGCTCTTAGATTATGACGATAATTATCATAGTATTGTTTT
ATACGATAACTAAGCAAGCGAATTTATTGATTAACTGCGAACCGAATAAA
TAAGTGATGAAGTGACATCGCATCCACTTTCAGGAAAAAATGGCAGACAC
AAATTGATATATGCAGGGAGAAACTTTACAGATATATGGGATTTTTTGTT
AATAACACGATGTTACATAAAGAAAACCACTCGGAGAAAATGGTGGCATA
AAGTAGAAAAGTTTGAGTTAACAAAAGGCATACAAGACAAAAGCTTTTGC
GATCGTGGGAAACCACTTTGATCTCAAATTAATTAATCATTCAGTCTTTA
TCATAATCCACAAAAAAACTTTATTTTACATGTTGTTCTCAAATAAAAAA
AACTTTTGATTTTCCTTTTCTTCTTTTAAATGAAGAAACTGCAATGTAAG
TTTCTTTTTTTTTTTGACAAAAATTGCAATGTAAGTTTTTTTTTTTGTAA
GCTAAAATTGTAATGTAAGTTTTGGCGTGGTTTCTTTGGACCATGCCTTT
TGCACCACCAGTGACCACCTGGCTTCGACAACTCAACGACATATAAGTCT
CATATTTTTTTGTAACGATTAATTTCACATTAC