Multinational Brassica Genome Project Steering Committee meeting

10am Sunday 14 January 2007

Crescent Rm, Town & Country Hotel, San Diego

Chair: Graham King

Participants (incomplete list)

members

| Graham King Chair MGBP Steering Committee 2005- | graham king@bbsrc.ac.uk | UK |
| --- | --- | --- |
| Dave Edwards | Dave.Edwards@dpi.vic.gov.au | Australia |
| Jacqui Batley | Jacqueline.Batley@dpi.vic.gov.au | Australia |
| Gijs van Rooijen | vanrooijen@genomeprairie.ca | Canada |
| Bin Liu | liub@genomics.org.cn | China |
| Boulos Chalhoub | chalhoub@evry.inra.fr | France |
| Beom-Seok Park | pbeom@rda.go.kr | Korea |
| Myung Ho Lim | mlim312@rda.go.kr | Korea |
| Yong Pyo Lim | yplim@cnu.ac.kr | Korea |
| Derek Lydiate | lydiated@agr.gc.ca | Canada |
| Isobel Parkin | parkini@agr.gc.ca | Canada |
| Andy Paterson | paterson@dogwood.botany.uga.edu | USA |
| Chris Town | cdtown@tigr.org | USA |
| Govind Garg | govindgarg@krishidhanseeds.net | India |

Other delegates:

| Andy Sharpe | sharpea@agr.gc.ca | Canada |
| --- | --- | --- |
| Raju Datla | Raju.datla@nrc-cnrc.gc.ca | Canada |
| Gopalan Selavaraj | Gopalan.selvaraj@nrc-cnrc.gc.ca | Canada |
| Faouzi Bekkaoui | Faouzi.bekkaoui@nrc-cnrc.gc.ca | Canada |
| Larry Pelcher | Larry.pelcher@nrc-cnrc.gc.ca | Canada |
| J. Chris Pires | piresjc@missouri.edu | USA |
| Anker Sørensen | anker.sorensen@keygene.com | NL |
| Jung Sun Kim | junkim@rda.go.kr | Korea |
| Yeon-Ki Kim | Kim250a11@gmail.com | Korea |
| Matthew Nelson | mnelson@plants.uwa.edu.au | Australia |
| Robert Tran | RKTRAN@UCDAVIS.edu | USA |
| Ian Bancroft | Ian.bancroft@bbsrc.ac.uk | UK |
| Federico L Iniguez-Luy | fliniguezluy@wisc.edu | USA |
| Gohataj | gohartajkhan@rediffmail.com | India |
| Rubens N. Tomita | rubens@affrc.go.jp | Japan |
| Christian Obermeier | Christian.obermeier@agrar-uni-giessen.de | Germany |
| Tae-Jin Yang | tjyang@snu.ac.kr | Korea |
| Soo-Jin Kwon | sjkwon@rda.go.kr | Korea |
| Mina Jin | genemina@rda.go.kr | Korea |
| Carlos Quiros | CFQUIROS@UCDAVIS.edu | USA |
| Reno Pontarollo | rpontarollo@genomeprairie.ca | Canada |
| Martin Trick | martin.trick@bbsrc.ac.uk | UK |
| Graham King | graham.king@bbsrc.ac.uk | UK |
| Lars Østergaard | Lars.ostergaard@bbsrc.ac.uk | UK |

Participants briefly introduced themselves

1.   Minutes of previous meeting, matters arising

Minutes of previous meeting were approved without revisions

2.   Inventory of public domain resources

Graham King (GK) sent out a questionnaire to Brassica researchers in February 2006, and then in December 2006. He received few replies that will be compiled and shared with the Brassica research community. GK enquired if there are other resources the participants wish to share. He has accumulated additional information about other resources (including from original survey 2002), but he will contact the relevant people first to ensure that the information is accurate and up to date before dissemination. Graham indicated that Rothamsted Research is hiring a Brassica data curator (part-funded from BBSRC AdVaB project), with start date in March or April. The curator will get in contact with contributors to update relevant information on the Brassica.info website.

3.   Data and nomenclature standards

As a result of the increasing convergence of information aligning linkage maps, chromosomes and genomic sequences, it was agreed that it was timely to assign consistent chromosome/linkage group nomenclature to the canonical diploid Brassica genomes in the 'triangle of U' as: 'A', 'B' and 'C'.

|  | A | B | C |
| --- | --- | --- | --- |
|  | A01 - A10 | B01-B08 | C01 - C09 |
| B. rapa | R1-R10 |  |  |
| B. nigra |  | G1-G8 |  |
| B. oleracea |  |  | O1-O9 |
| B. juncea | J1-J10 | J11-J18 |  |
| B. napus | N1-N10 |  | N11-N19 |
| B. carinata |  | ? | ? |

In order to ensure that this is universally agreed and adopted, it was agreed that it would then be necessary to a) publish a short paper describing the definitive nomenclature system in a recognised journal; b) notify key Journal editors;  and c) also to publicise this more generally on websites/mailing lists etc.

- Derek Lydiate agreed to follow-up with concerned participants to draft the note on nomenclature for publication.

- This would include collation of existing major maps where available, and describe the resources necessary and available to verify chromosome identity. This would include the relevant populations and key sequence-tagged markers/allelic information to required to verify.

- Derek would contact the Rennes group to confirm their agreement, and also to enquire re: status of existing B. juncea map/population (Lionneton et al., 2002).

- Andrew Paterson suggested that any publication should include a translation table relating to existing published maps where these had been integrated.

4.   Diversity sets

This topic was addressed in the TILLING meeting.

B. oleracea

Warwick-HRI (UK) developed B. oleracea fixed lines. The process is being finished though it is taking longer than expected. WHRI is working on 188 lines.

Seed and DNA available for founder lines. Contact: graham.teakle@warwick.ac.uk

B. napus

188 fixed lines are being developed at HRI in collaboration with Rothamsted Research (UK) as part of the OREGIN project. DNA is available publicly. 50 of 94 lines seeds are available to date.

Seed and DNA available for founder lines. Contact: graham.teakle@warwick.ac.uk

B. rapa

Guusje Bonnema  (WUR, The Netherlands)/Xiaowu Wang (CAAS, Beijing) and Graham King (Rothamsted, UK)  have identified 188 B. rapa founder lines. Graham invited people interested in helping with process or those developing diversity lines to contact him or contact Guusje Bonnema  to update information on resources. Dave Edwards indicated that B. napus and B. juncea diversity lines are also available from Australia.

In the wider context: Chirs Pires is assembling a collection of material representing a wider distribution within the tribe Brassicaceae.

5.   Report on TILLING consortia

The MBGP TILLING consortia held a meeting prior to this one. Lars Ostergaard gave an update on the TILLING consortia including consortia members, aims, distribution of resources and web design. Minutes from the meeting and contact info will be posted on the TILLING website. (www.brassica.info/resources/tilling/mbgptc.htm)

6.   ESTs update

Currently there are approx. 163,750  Brassica ESTs in GenBank, an increase of ~40,000 during 2006. The number of Brassica ESTs to be available in GenBank will increase significantly during 2007, as a result of discussions during 2006 associated with providing sufficient information to develop a good representative transcriptional array. By June 2007, there will be 447,000 B. napus ESTs and a total of 623,000 total Brassica ESTs from B. napus, B. rapa, B. juncea and B. carinata.

GK indicated that there will be a link on the brassica.info website to provide updates on Brassica ESTs (http://www.brassica.info/mbgp/mbgp1.htm). Martin Trick agreed to provide additional link to current sequence data held in BrassicaDB (which also has a BLAST server that allows any sequence to be searched against all current Brassica sequences, or the Arabidopsis genome). GK enquired if the participants are aware of other institutions that have not deposited Brassica ESTs in GenBank yet. He suggested that private companies (e.g. Bayer, BASF, Dow) may now be in a position to deposit ESTs now that there are is significant and good representation of sequences depositited by other institutions and consortia.

7.   Transcriptional arrays: MBGP Affymetrix chip, and others

Graham reported that during 2006 there had been considerable discussion about the design and preparation of the Brassica Community Affymetrix chip. In order to ensure that sufficient ESTs were available for the design, the original timeline was extended. This has allowed several groups to adapt their release programme into the public domain, with a target date of June 2007. He informed the participants about the Affymetrix meeting at PAG on Tuesday 8 pm. He invited the participants who are interested in the Brassica chip to interact with Affymetrix during the design to ensure a good quality chip.

Participants suggested inclusion of probes sequences from pathogen species and other probes to distinguish Brassica paralogues and/or homeologues as a separate set. It was agreed that these sequences could be included if there is space on the 45k chip and if it does not increase significantly the cost of the Brassica array. This was discussed further in the subsequent meeting with Affymetrix (notes of meetings to be posted at (www.brassica.info/genechip/genechip1.htm)

8.   Update on sequencing and genomics funding

Technical details on the B. rapa sequencing will be discussed at the meeting following this one. Yong Pyo Lim reported that the first phase of the MBrSP project was completed during 2006.

This has included:

- 200,000 BAC ends sequences from 110,000 clones have been completed thanks to the contributing institutions from: Australia, Canada, Germany, Korea, USA, UK.

- 510 + 60 seed BACs have been sequenced (Korea, with a few from Australia)

BAC by BAC sequencing of individual chromosomes has now commenced:

R1 	UK + China consortium, funded, 2007-2010

R3	Korea, funded, completion end 2007

R6	USA, proposal submitted, awaiting outcome N. hemisphere spring 2007

R7	Australia, funded, complete end 2007 (using 454 shotgun of BAC pools + 	Sanger finishing)

R8	UK + China consortium, funded, 2007-2010

R9	Korea, funded, complete end 2008

(status provided at http://www.brassica.info/b_rapa_sequencing_project/bac_sequencing.htm)

- Dave Edwards (Australia) indicated that Australia has completed the sequencing so far of 68 BACs, and has to complete the remaining BACs by the end of this year.

- GK suggested compiling the DNA sequencing statistics and posting on the Brassica.info website.

- USA: Chris Town indicated that sequencing of R6 chromosome proposal was submitted. The review panel will meet by the end of this month. He will update the review panel about the recent deposition of Brassica ESTs in GenBank which will likely help the proposal.

- Canada: Isobel Parkin  indicated that no funding is available yet to sequence R?1 and R10. However, a proposal will be submitted in 2007 with possible funding start in 2007 if proposal is successful.

- France: Boulos Chalhoub indicated that he is a funding call, and will be submitting a proposal in May 2007 to sequence 200, BACs with funding results to be announced in September. Information on BAC positions within chromosomes was not available.

- Germany: no update was available. (check Bernd)

- India:  Govind Garg indicated that India is interested in contributing to the sequencing effort.  Gopalan Selvaraj indicated that he visited recently India and funding of the sequencing of 1 chromosome is promising. It was suggested to contact Dr M.K. Bhan, Secretary, Department of Biotechnolgy, Govt. Of India, CGO ComplexII, Lodhi Road, New Delhi.

Other sequencing efforts:

- UK:  Ian Bancroft informed the participants that the UK-China consortium will sequence 72,000 B. napus BAC ends (in pSAC vector), and make these publicly available during 2007.

- USA: Chris Pires indicated that his group have received NSF funding to sequence  BACs from B oleracea  as part of a comparative analysis

9.   Summary of publicly available data from MBrSP (see also MBrSP management committee following this meeting)

This item was discussed in the following meeting.

10.  Upcoming international meetings

- Rapeseed Congress, Wuhan, China in March 2007

- PAG, San Diego, USA, January 2008

- ISHS Brassica meeting & Crucifer Genetics Workshop in Norway, Sep 2008 (Scientific Committee and Programme to be announced March 2007).

- Crucifer Genetics Workshop in Saskatoon 2010

11.  Information dissemination

- As indicated above, the BBSRC 'AdVaB' and sequencing projects in the UK will provide a data curator to update the brassica.info website. This work will include updating the inventory of public domain resources, as well as data for genetic map integration and consensus markers. Discussions are ongoing amongst several groups (e.g. AgVic, Melbourne - BASC; Georgia - ) for collating brassica data sources, and to make sure there are definitive data sources.

- It was suggested that a mailing/contact list be made available. For this to be possible, each member of existing list would need to agree for their information to be public. GJK indicated that this may be possible to manage as part of the data curator work at RRes.

- The possibility of collating bibliographic information was suggested. However, this is an onerous task and probably sufficient added value compared to individuals carrying out online searches. There may be several text-mining approaches that could be suitable if funded.  Alternatively, key papers could be collated and highlighted as part of the data collation on brassica.info relating to reference resources and information. The possibility of sharing End-Note libraries was suggested.

10.  Election of Chair (agreed remit states every two years)

A committee chair is elected every 2 years. Ian Bancroft (UK) was the first chair of this committee. Graham King (UK, current chair, 2005-7) was due to step down, and called for nominations. Isobel Parkin (AAFC, Canada) was nominated. All participants were in favour of the nomination. Ian Bancroft and the participants thanked Graham King for serving as chair in the last 2 years.

- AOB

none

Meeting was formally adjourned at 12:25 pm

Minutes prepared by GJK from notes kindly taken by Faouzi Bekkaoui