MBGP Steering Committee

1/10/2006 Crucifer Genetics Workshop, WICC, Wageningen, NL.

Attendees

| Barker, Guy | guy.barker@warwick.ac.uk | UK |
| --- | --- | --- |
| Batley, Jacqui | jacqueline.batley@dpi.vic.gov.au | Australia |
| Bekkaoui, Faouzi | Faouzi.Bekkaoui@nrc-cnrc.gc.ca | Canada |
| Bonnema, Guusje | guusje.bonnema@wur.nl | Netherlands |
| Cowling, Wallace | wcowling@cyllene.uwa.edu.au | Australia |
| Datla, Raju | raju.datla@nrc.gc.ca | Canada |
| Edwards, Dave | dave.edwards@dpi.vic.gov.au | Australia |
| Friedt, Wolfgang | wolfgang.friedt@agrar.uni-giessen.de | Germany |
| Hirai, Masashi | mhirai@kab.seika.kyoto.jp | Japan |
| Holtgraewe, Daniela | dholtgra@cebitec.uni-bielefeld.de | Germany |
| Keller, Wilf | wilf.keller@nrc.gc.ca | Canada |
| Kim, Jin A | jakim@rda.go.kr | Korea |
| Kim, Jung Sun | junkim@rda.go.kr | Korea |
| King, Graham | graham.king@bbsrc.ac.uk | UK |
| Matsumoto, Satoru | Ssmats@affrc.go.jp | Japan |
| Meng, Jinling | jmeng@mail.hzau.edu.cn | China |
| Park, Beom-Seok | pbeom@rda.go.kr | Korea |
| Parkin, Isobel | parkin@agr.gc.ca | Canada |
| Renard, M | renard@rennes.inra.fr | France |
| Sadowski, Jau | jsad@amu.edu.pl | Poland |
| Sharpe, Andy | sharpea@agr.gc.ca | Canada |
| Trick, Martin | martin.trick@bbsrc.ac.uk | UK |
| Yang, Tae-jin | tjyang@snu.ac.kr | Korea |

Apologies A. Patterson; B.Weisshaar, C. Pires

Notes of previous meeting (Jan 2006) available: http://www.brassica.info/meetings.htm

1.	B. rapa Sequencing: chromosome assignment as of 1/10/06

R3 and R9 being sequenced by Korea.

R7 Australia commenced

R1 and R8 assigned to U.K. and China (China funding approved, UK awaiting decision)

R6 USA (application submitted Oct 2006)

R2 and R10 assigned to Canada

Other contributions:

Netherlands possible submission as part of a new programme (G.Bonemma)

France to submit proposal March 2007 to sequence 250 BACS as part of their National programme (MR)

India - unknown status

2. 	Update on progress of B. rapa sequencing

- Both B.rapa libraries now fully end sequenced and data from all laboratories submitted to GenBank. 200,553 end sequences are now in GenBank

- SnapShot high resolution fingerprinting by NIAB Korea, being carried out on 100,000 clones will be finished Sept 2006. A report on this will be submitted at PAG in January. Data will be released in FPC format DB.

- 500 BAC sequences have been submitted or are in progress. The lists of these and their status is available at http://www.brassica-rapa.org/brgp_main/jsp/public_seq.jsp. 200 have been completed and are submitted to Genbank.

- Estimated dates for completion:

  - R3 end 2007

  - R9 end 2008

  - R7 end 2007

3.	B. rapa linkage group assignment

- 390 of the seed BACs have been genetically mapped (JWF3 and/or CKDH populations).   250 by SSR; 50 RFLP; 20 CAPS; 70 Ctg

- Screening carried out initially in JWF3p then sent to YPL (CNU, Korea) for mapping in CKDH. DNA from JWF3p is available -  will be sent to DE (AgVic, Australia) asap. Information on mapping genotype strings will be made available to individual labs through personal communication. Publication aimed to be finished by end of year then full release.

- SSRs from 'Suwabe' map have been used to identify and associate B. rapa linkage maps

- Further markers to be assigned by AAFC Saskatoon to Jw map to help confirm any ambiguities in Linkage group assignment.

3.	EST update

In addition to the approx 120,000 Brassica ESTs currently in Genbank:

- NRC (PBI) in Canada have undertaken to release approx. 245,000 (seed-derived) B. napus ESTs by June 30, 2007; 62,000 have already been released and an additional 15,000 to be released by January 1, 2007 and 167,000 to be released by June 30, 2007

- AAFC are also prepared to release to this timescale.

- The NIAB group in Korea are also now amenable to releasing their B. rapa EST in a similar time-frame and under equivalent conditions (embargo until June 2007).

- The AgVic Australia group will also deposit 20,000 ESTs in this timeframe.

4.	Brassica micro-arrays

- Update on Affymetric Brassica GeneChip (R).

Discussions led to decision to delay design until EST data from NRC Canada and Korea becomes available - this would greatly increase gene coverage. The planned release date would be now be June 2007, dependent upon confirmation from Affymetrix.

Other arrays

Nimblegen chip    23K array now available from Korea

- contact Myung-Ho Lim (NIAB, Korea)

email : mlim312@rda.go.kr (Tel : +82-31-299-1675)

AAFC 1		5K double spotted oligo array avalibale

NRC 		10K cDNA array will be released when ests are July 2007

AAFC and NRC 	are in discussion on production of CombiMatrix oligo array

5.	MBGP TILLING Consortium

- Lars Ostergaard (JIC, Norwich UK) is leading this consortium with a sub-committee, and has collated information from different groups worldwide.  (Table below)

- Discussion to be held in San Diego after MBGP meeting to discuss any potential difficulties creation of a TILLING network may present. This will include discussion of reciprocal access charges from non-members,  balance of private versus public, etc. Michel Renard suggested that maybe too many B.napus populations being made as number of lines required small due to mutational load. Circulate report on population size required.

6.	Diversity sets

B. oleracea, C genome and B.napus sets are well under way (WHRI). B.rapa design to be circulated for comment by GK G.Bon and XW - aiming for 200 lines.

7.	Informatics and Data Standards

A sub-committee of MBGP was initiated led by Dave Edwards (Agvic, Australia).  A brief initial meeting was established in Wageningen with the aim to provide a means to harmonise data sources, and provide clear minimal sets of information, especially relating to the B. rapa sequencing project. It was agreed that regular summary spreadsheets of current sequencing status would be made available and posted on www.brassica.info.

8.	Other Business

Decision to create sub committee to discuss data management and data standards. First meeting to be held 2/10/06.

Next meeting

Sun Jan 14th 2007, PAG San Diego - room to be announced

Also meeting of B. rapa Sequencing Steering Group to be held after MBGP SC meeting, and meeting of MBGP TILLING consortium before or after the MBGP SC meeting.